## Sheet1
Scrum Backlog & Stories
Weeks | Task | Story Points | Task Owner | Working Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Week 1 02/17-02/23 | Project planning & backend logic discussion | 8 | Ranyi | 5 | 2 | 1 | 0 | 0 | 1 | 1 | 1
| Draft initial schema for restaurant modules | 8 | Tingfei | 5 | 1 | 2 | 0 | 0 | 2 | 2 | 0
| Outline design structure & burndown chart | 8 | Sheetal | 5 | 1 | 1 | 1 | 0 | 2 | 1 | 0
| Document tech stack discussions | 4 | Kawal | 4 | 2 | 1 | 0 | 1 | 0 | 1 | 1
Week 2 02/24-03/02 | Initial models & migrations for restaurants, users, bookings, reviews Implement login, registration, and user roles in backend | 12 | Ranyi | 7 | 0 | 1 | 0 | 0 | 1 | 1 | 1
| Draft initial models and migrations for bookings and reviews | 12 | Tingfei | 7 | 0 | 1 | 1 | 1 | 0 | 1 | 0
| Set up React app, routing, layout | 10 | Sheetal | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 1
| Organize backlog & sprint notes | 3 | Kawal | 4 | 2 | 1 | 0 | 1 | 0 | 0 | 2
Week 3 03/03-03/09 | Implement CRUD API for restaurants | 13 | Ranyi | 6 | 2 | 0 | 1 | 1 | 0 | 2 | 0
| Implement CRUD API for bookings | 9 | Tingfei | 6 | 1 | 0 | 2 | 1 | 1 | 0 | 1
| Implement frontend login, registration, and navigation | 8 | Sheetal | 6 | 1 | 0 | 0 | 1 | 0 | 1 | 1
| Review & annotate diagrams | 4 | Kawal | 4 | 1 | 0 | 2 | 0 | 1 | 1 | 1
Week 4 03/04-03/16 | Implement admin/manager endpoints for users | 6 | Ryan | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| Implement CRUD API for reviews | 6 | Tingfei | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1
| Implement restaurant listing, detail, and booking pages (frontend) | 6 | Sheetal | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Check README structure & visuals | 2 | Kawal | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0
Week 5 03/17-03/23 | Implement filtering/search endpoints for restaurants and bookings | 8 | Ryan | 5 | 1 | 0 | 0 | 0 | 1 | 1 | 0
| Implement analytics endpoints (bookings, reviews) | 8 | Tingfei | 5 | 0 | 2 | 0 | 0 | 1 | 1 | 1
| Implement advanced filtering/search UI (frontend) | 8 | Sheetal | 5 | 3 | 1 | 2 | 0 | 0 | 1 | 0
| Review analytics section formatting | 5 | Kawal | 6 | 0 | 1 | 1 | 1 | 0 | 2 | 1
Week 6 03/24-03/30 | Integrate email/SMS notifications in backend | 8 | Ryan | 5 | 2 | 1 | 3 | 0 | 0 | 1 | 0
| Integrate booking status, review status, and analytics in backend | 7 | Tingfei | 5 | 0 | 1 | 0 | 1 | 0 | 0 | 0
| Implement booking form, review form, and notification UI (frontend) | 5 | Sheetal | 4 | 0 | 0 | 0 | 1 | 1 | 0 | 2
| Organize Week 6 sprint notes | 5 | Kawal | 3 | 1 | 0 | 0 | 0 | 1 | 2 | 0
Week 7 03/31-04/06 | Implement admin/manager dashboards (backend endpoints) | 10 | Ryan | 6 | 2 | 0 | 0 | 0 | 0 | 3 | 1
| Implement customer dashboard endpoints (backend) | 10 | Tingfei | 4 | 0 | 1 | 0 | 1 | 0 | 1 | 1
| Implement admin/manager/customer dashboards (frontend) | 8 | Sheetal | 5 | 1 | 0 | 1 | 1 | 1 | 1 | 0
| Compile retrospective notes | 8 | Kawal | 5 | 1 | 1 | 0 | 1 | 2 | 0 | 0
Week 8 04/07-04/13 | Prepare deployment scripts, settings, and static file handling | 3 | Ryan | 4 | 0 | 1 | 0 | 0 | 2 | 0 | 1
| Prepare database seeding, migration, and backup scripts | 8 | Tingfei | 7 | 3 | 1 | 0 | 1 | 0 | 2 | 0
| Finalize frontend build and deployment scripts | 8 | Sheetal | 6 | 0 | 2 | 2 | 0 | 2 | 0 | 0
| Review documentation index | 5 | Kawal | 4 | 0 | 1 | 1 | 1 | 0 | 0 | 1
Week 9 04/14/-04/27 | Conduct end-to-end functional testing for the entire application. | 11 | Ryan | 8 | 3 | 1 | 0 | 1 | 0 | 1 | 1
| Deploy the frontend to hosting services | 13 | Tingfei | 8 | 1 | 1 | 1 | 1 | 2 | 2 | 0
| Ensuring all features are working | 10 | Sheetal | 8 | 1 | 2 | 0 | 1 | 0 | 1 | 3
| Contribute to final project report | 5 | Kawal | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 1
Total |  | 270 |  | 180
Team Members | Working Hours
Ranyi | 6 hr/week
Tingfei | 6 hr/week
Sheetal | 6 hr/week
Kawal | 2 hr/week
Total Working Hours | 180